## Resource List
Resource ID | Resource Name | Resource Type | Department | Availability (hrs/week)
R001 | Alice Johnson | Developer | IT | 40
R002 | Bob Smith | Designer | Creative | 35
R003 | Charlie Lee | QA Engineer | QA | 40
R004 | Diana Prince | Project Manager | Management | 30

## Project Assignments
Department | Project Name | Task Name | Resource Type | Resource Assigned | Start Date | End Date | Hours Allocated | % Allocation | % Utilized
IT | Alpha | Development | Developer | Alice Johnson | 2025-04-10 | 2025-04-24 | 60 | 75 | 150%
Creative | Alpha | UI Design | Designer | Bob Smith | 2025-04-11 | 2025-04-20 | 40 | 65 | 114.3%
QA | Beta | Testing | QA Engineer | Charlie Lee | 2025-04-15 | 2025-04-30 | 50 | 65 | 125%
Management | Beta | Project Planning | Project Manager | Diana Prince | 2025-04-12 | 2025-04-18 | 30 | 50 | 100%

## Resource Load Summary
Resource Name | Availability (hrs/week) | Hours Assigned | % Utilized | Over-Allocated?
Alice Johnson | 40 | 60 | 150% | Yes
Bob Smith | 35 | 40 | 114.3% | Yes
Charlie Lee | 40 | 50 | 125% | Yes
Diana Prince | 30 | 30 | 100% | No

## Pivot Tables
Resource Assigned | Sum of Hours Allocated |  | Department | Sum of Hours Allocated
Alice Johnson | 60 |  | Creative | 40
Bob Smith | 40 |  | IT | 60
Charlie Lee | 50 |  | Management | 30
Diana Prince | 30 |  | QA | 50
Grand Total | 180 |  | Grand Total | 180
Sum of Hours Allocated | Resource Assigned
Project Name | Alice Johnson | Bob Smith | Charlie Lee | Diana Prince | Grand Total
Alpha | 60 | 40 |  |  | 100
Beta |  |  | 50 | 30 | 80
Grand Total | 60 | 40 | 50 | 30 | 180

## Dashboard
RESOURCE ALLOCATION DASHBOARD
KPI Cards for this Project ==> | Total Projects | Total Resources | Overallocated People | Avg. Utilization
| 2 | 4 | 3 | 122.3%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.