## Risk Data
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Mitigation Plan | Risk Score | Risk Level
R1 | Scope creep due to unclear requirements | 4 | 5 | Clarify and freeze requirements early | 20 | High
R2 | Key team member resignation | 3 | 4 | Cross-train team members | 12 | Medium
R3 | Budget overrun | 5 | 4 | Monitor budget weekly | 20 | High
R4 | Vendor delay in delivery | 2 | 3 | Set early deadlines for vendors | 6 | Low
R5 | Data security breach | 4 | 5 | Implement strict access controls | 20 | High

## Risk Matrix
| 1 | 2 | 3 | 4 | 5
1 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 1 | 0 | 0
3 | 0 | 0 | 0 | 1 | 1
4 | 0 | 0 | 0 | 0 | 2
5 | 0 | 0 | 0 | 1 | 0

## Pivot Table
Risk Level | Count of Risk Level
High | 3
Low | 1
Medium | 1
Grand Total | 5
Count of Risk ID | Impact(1-5)
Likelihood(1-5) | 3 | 4 | 5 | Grand Total
2 | 1 |  |  | 1
3 |  | 1 |  | 1
4 |  |  | 2 | 2
5 |  | 1 |  | 1
Grand Total | 1 | 2 | 2 | 5

## Dashboard
Project Risk Assessment Dashboard
Risk Matrix Table
Risk ID | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level
R1 | 4 | 5 | 20 | High
R2 | 3 | 4 | 12 | Medium
R3 | 5 | 4 | 20 | High
R4 | 2 | 3 | 6 | Low
R5 | 4 | 5 | 20 | High
Key Insights Summary
Total Risks: 5 risks have been assessed.
Risk Distribution:
High Risk: 3 risks need urgent attention.
Medium Risk: 1 risk requires close monitoring.
Low Risk: 1 risk is manageable with minimal intervention.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.