## Milestone Tracker
Project Name | Milestone ID | Milestone Name | Start Date | End Date | Duration (Days) | Status | Completion (%) | Comments | Progress | Progress Value
Project A | 1 | Initiation | 2025-04-01 | 2025-04-05 | 4 | Completed | 100% | Finish | Completed Progress | 37.5%
Project B | 2 | Planning | 2025-04-10 | 2025-04-15 | 5 | In Progress | 50% | Planning in progress | Remaining Progress | 62.5%
Project C | 3 | Execution | 2025-04-20 | 2025-04-30 | 10 | Not Started | 0% | Pending
Project D | 4 | Closure | 2025-05-01 | 2025-05-05 | 4 | Not Started | 0% | Pending
37.5%

## Gantt Chart Data
Milstone Names | Start Date | Duration(Days)
Initiation | 2025-04-01 | 4
Planning | 2025-04-10 | 5
Execution | 2025-04-20 | 10
Closure | 2025-05-01 | 4

## Dashboard
Project Milestone Tracker Dashboard
KPI Summary Table
Metric | Value
Total Milestones | 4
Completed Milestones | 1
In Progress Milestones | 1
Not Started Milestones | 2
Overdue Milestones | 1
Overall Completion % | 37.5%
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Key Features:
Automated Milestone Tracking with status and completion indicators.
KPI Summary Table showing total, completed, in-progress, not started, and overdue milestones.
Overall Completion Calculation for real-time progress monitoring.
Gantt Chart Visualization for milestone timelines.
Dynamic Dashboard Layout designed for clarity and executive-level insights